## Sheet1
Socheath Sok | React Native basic, Github |  |  | Presentation | Summaries | HW milestones | SW milestones
|  | Friday | 2019-09-20 |  |  | finalize parts list
Jas | sensor/microcontroller | Sunday | 2019-09-22 |  |  | order parts
|  | Monday | 2019-09-23 |  | PR 1 | Know how to connect microntroller to sensor and wireless communication module
Rhyan | Hardware/ battery
|  | Monday | 2019-09-30 | constraint |  | Parts arrival
Calvin | wireless communication
| how info transfer between devices | Monday | 2019-10-07 |  |  |  | UI design complete
|  | Monday | 2019-10-14 | Requirement |  | Helmet assembled
|  | Monday | 2019-10-21 |  | PR 2
|  | Monday | 2019-10-28 | Req. Trace
|  | Monday | 2019-11-04 |  |  |  | app function complete
|  | Monday | 2019-11-11 | Design
|  | Monday | 2019-11-18
|  | Monday | 2019-11-25 |  | PR 3
|  | Monday | 2019-12-02 | Demo